## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Sivanandini | 2025-11-12 | Registration form allowed submission without mandatory fields | Sprint 1 | Sivanandini | Functional | Added input validation for mandatory fields | 2025-11-13 | Closed | Working as expected
2 | Sivanandini | 2025-11-14 | Model accuracy was lower than expected on unseen data | Sprint 2 | Sivanandini | Model/Algorithm | Tuned hyperparameters & applied feature scaling | 2025-11-15 | Closed | Accuracy improved
3 | Sivanandini | 2025-11-16 | UI misalignment issue in mobile view | Sprint 3 | Sivanandini | UI/UX | Updated CSS & tested responsiveness | 2025-11-17 | Closed | Verified
4 | Sivanandini | 2025-11-17 | Application error when entering special characters in income field | Sprint 3 | Sivanandini | Input Validation | Added regex validation & sanitization | 2025-11-18 | Closed | Works fine now
5 | Sivanandini | 2025-11-18 | Page loading delay after model prediction | Sprint 4 | Sivanandini | Performance | Optimized backend logic & reduced I/O calls | 2025-11-19 | Closed | Performance improved

## Sheet2
Logical
User Interface
Maintainability
Standards
Others