## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Tester_A | 2025-09-28 | Streamlit form issue | Sprint 1 | Frontend | UI Bug | Minor UI tweaks applied | 2025-09-29 | Closed | Validation logic corrected and functioning smoothly.
2 | Tester_B | 2025-09-30 | One-hot encoding bug | Sprint 1 | Backend | Functional Bug | Fixed preprocessing code | 2025-10-01 | Closed | Encoding pipeline refined for stability.
3 | Data_Lead | 2025-10-12 | Random forest training issue | Sprint 2 | ML | Performance | Hyperparameter tuning applied | 2025-10-15 | Closed | Model validation accuracy increased to 81%.
4 | Tester_A | 2025-10-24 | SHAP display problem | Sprint 3 | Frontend | UI Bug | Updated SHAP integration | 2025-10-25 | Closed | Layout aligned well and renders correctly now.
5 | Tester_B | 2025-10-28 | PDF export bug | Sprint 3 | Backend | Functional | Updated PDF generation code | 2025-10-30 | Closed | UTF-8 characters now appear properly in the PDF.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others